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Timetable for Drainage Works 

Condition 12 

"Within 3 months of commencement of development, the following details shall be submitted to and approved in writing by the local planning authority: 
• a timetable for the implementation of the foul sewerage and sustainable surface water drainage systems to serve the development; 
• final details of the profile, levels, sections and construction of the drainage pond to be located towards the south-eastern corner of the site; and 
• details of the final design of the proposed pumping station, including the extent of any associated excavations which, unless otherwise agreed in writing by the local planning authority, shall take place outside of the root protection areas of the adjacent trees and under arboricultural supervision. 

The foul and surface water drainage provisions for the site shall then be carried out in accordance with these approved details along with those contained within the submitted Flood Risk Assessment and Drainage Strategy (Paul Basham Associates, 199.5002/FRA&DS/5, January 2022), and Drawing Numbers: 199.5002.151 Revision C, 199.5002.501 Revision B (Sheet 1 of 2), 199.5002.501 Revision B (Sheet 2 of 2), 199.5002.503 Revision G (Sheet 1 of 2), 199.5002.504 Revision G (Sheet 2 of 2)."

This note covers the first bullet point of condition 12 relating to the timescales for implementing both the foul and surface water drainage systems. 

Pre Start works 
A Section 278 agreement is required for the works and has been submitted to HCC.  

Commencement on Site 
The roads will be installed as per the approved plans with the drainage and storm water infrastructure being completed in one phase. 

The delivery of the road is anticipated to take approximately 3 months with a further 2 months to build pump station and the pond. 


Completion 
Approx 5 months from starting works on site. 

Conclusion 
The proposed drainage system are anticipated to take a period of 5 months from the date of works starting on site. This is dependent on weather and site conditions. The drainage systems will be constructed and operational prior to the occupation of the first dwelling. 
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