## Sheet1
Boorley Gateway - Conditions 15, 17, 19 Landscape Comments and actions.
Date: 16/12/24 Rev C
Item | Comment | ACD Response | Vistry Response | Tim Griffin comments 13th June 2024 | Landscape Consultant/Client comments 05.09.24 | TG comments 12th Sept. 2024 |  | TG comments 16th Jan. 2025
1 | check the consistency between all the plans and confirm they are correct. | Noted
2 | We seem to have two hard landscape plans for the northern area. They differ in the design of the shopping precinct area, yet have the same date and drawing number and neither has a revision note and letter. Please clarify which is the correct one and ensure that the soft landscape plans in the vicinity of the shopping precinct correlate with the correct version |  | See attached Hard Landscape plans VYH23647 12 Sheet 1 - 4
3 | Please can ACD amalgamate their landscape and open space plans in future? | Noted
Soft Landscape Resi -Series 11
1 | Specification for topsoil in tree pit detail; use of BS3882:2015 requires a little more detail. | VYH23647 Soft landscape Specification section 4.13 provides greater detail on backfill of tree pit. | See attached soft landscaping plans VYH23647 11 Sheet 1 - 4 | Landscape specification note 4.13 is not clear - for trees in hard landscape - please specify Rootsoil not structural tree soil. Tree pit detail hard landscape on landscape plans shows Rootsoil. | Completed
VYH23647 11 Sheet 1 | Please add in screen planting to the east and south of the brick wall as identified in Tim Griffin’s comments previously | As illustrated and discussed/agreed with Tim previously there is planting in place both in the form of a formal hedgerow, climbers, specimen trees and shrub planting bed. |  | I think there is some mis-understanding here - at present the outside face of the brick wall (facing the footpath) is only softened with 3 climbers which is insufficient. My comments & markup dated 14th Jan 2021 showed shrub planting here. Please re-visit. Also note my markup comment ref. tree planting in this location with a single larger specimen (Corylus colurna) relocated centrally to the space and the other tree (Pyrus spp.) moved to footpath side of the bw among shrub planting. | The LA700F landscape proposals do not illustrate shrub planting against or adjacent to the outer wall. The proposed climbers to the outer wall number 5 in total and over time will mature, grow and form a denser coverage of the space. | Changes still outstanding - see email from Liz. H. requesting further changes - there is reference to the need for further planting between the garden wall and the footpath to the north-east/east of the wall and amendments to the tree planting in the garden area. As set out in my email dated 9.9.24 (copy attached) this is in relation to the wording of condition 15 and these comments do need to be addressed. | Plan amended
VYH23647 11 Sheet 2 | Some of the labels on the eastern side of the drawing are obscured. Please reposition image to remedy this. | Update to comment. |  | This issue has not been satisfactorily resolved - some tree species still omitted on overlapping sheets e.g. overlap sheets 2 & 3 - tree to E of rear of Plot 13 in parking court. Please check all sheets. For future planting plans please improve on the arrangement of overlapping sheets by including a key plan on all sheets that indicates site coverage and locations sheet by sheet. (Similar to key diagram on Sheet 4 Hard Landscape Proposals drawing - need similar keys on all plans so easy to work coverage across site). | Noted - but not a requirement of condition.
VYH23647 11 Sheet 3 | Some of the labels on the western side of the drawing are obscured. Please reposition image to remedy this. | Update to comment.
VYH23647 11 Sheet 4 | Some of the labels on the eastern side of the drawing are obscured. Please reposition image to remedy this. | Update to comment.
Soft Landscape Open Space- series 21 |  |  |  | No revised OS series 21 plans have been uploaded on Salesforce rec/d 10.5.24 so I assume these drawings have not been revised | Revised series 21 Plans provided
VYH23647 21 Sheet 1
1 | Some of the trees around the margins of the drawing don’t seem to be labelled. | All trees contained within the planting schedule are specified within the drawing, the unspecified trees are referenced locations of trees specified within the Soft landscape VYH23647 11 drawings. |  |  | Revised series 21 Plans provided
2 | Car park and site frontage trees. There are a few issues with the line of Oaks. They will ultimately grow very large. In view of the north-east orientation of the shops a smaller tree would be better so as to reduce shading of the area, although it is agreed that a large tree is still required | The planting palette is in accordance with the details agreed in the outline proposals and these have subsequently been adjusted to previous comments received and now reflect this input. |  |  | Revised series 21 Plans provided
VYH23647 21 Sheet 2
1 | The minimum stock size acceptable for trees is 14-16cm girth (except for trees in rear gardens, which may be smaller). Please amend the schedule. | The planting palette is in accordance with the details agreed in the outline proposals. |  |  | Revised series 21 Plans provided | Some trees still specified as 12-14cm stock. Please change to 14-16cm girth unless in rear gardens | Plan amended
General comments on soft landscape and open space sheets
1 | Hedges to have strained wire fence along centreline to prevent shortcutting and damage to planting. | This is already stated within the key. |  |  | Completed
2 | Please identify the seat type in the keys where shown. Other sheets identify this as by Proludic RBA 1. The make is fine, but the style is not great with the style of architecture. Please change to Proludic RBA 8 |  | Information on bench already sent for condition 16 - please see details of the materials used. • Cast-iron legs and armrests with anti-oxidizing primer and black oxyron finish. • Hot-dip galvanised screws • Exotic wood o WOOD SUCUPIRA o LASURE CAOBA fungicide treatment o IRURERA GLAZE BRAND All our wood used is FSC certified. | Bench approved.
VYH23647 14 sheet 1: Landscape construction details
3 | Please provide details of the timber to be used for the bollards. | Hardwood Treated Timber Bollard 125x125x750mm with reflectors. |  | Update hard landscape plans to match as presently key shows 0.6m high bollards. | Completed | Hard landscape plans appear to still show 750mm bollards while the construction details show 500mm high bollard? Please resolve |  | Please confirm that if bollards only 500mm above G.L. will not create safety hazard for pedestrians and vehicles.
4 | Please replace the typical knee rail detail with a galvanised and black powder coated mild steel version |  | Vistry have confirmed that they wish to retain the timber knee rail | Hard landscape plan indicates metal trip rail - a timber knee rail detail is not an acceptable long-term solution. EBC have years of negative experience with the ugly and short lived 'birds mouth' timber knee rail detail. Please use only metal knee rail detail. | Timber knee rails have been used on the main site and approved - see Parcels B3a, B4, B5, B6, C3 & C7
5 | Hedges to have strained wire fence along centreline to prevent shortcutting and damage to planting. Please provide a detail for this add a location symbol to all relevant plans. |  | This is already stated within the key. | The note on the key will likely be missed by contractors. Please add detail on the landscape construction sheet as requested. Also add symbol on plans and change key note to read - Where hedge not backed by wall or fence 0.9m high post and three strained wire fence with driven (not concreted) posts installed along centreline of hedge before planting. | Completed, addressed previously, comments relate to a previous version of our plan
Landscape specification
1 | There are several incidences of the use of the phrase ‘shall only be permitted with the strict approval of the Architect’ or similar wording. E.g. paras 1.10; 1.16; . These should be changed to read ‘Landscape architect’. We would also require evidence that ACD or another landscape architect independent of the landscape contractor will be retained to monitor the correct implementation of the works. | Phrasing to be adjusted, client to confirm monitoring the correct implementation of the works. | ACD confirmed as retained to monitor the correct implementation of the works.
2 | Para 1.6 -I’m not keen on the weed clearance method because it is not likely to be successful in killing persistent and deep-rooted weeds. Please amend to include a treatment of a systemic herbicide some weeks during the growing season after the initial brush cut. We should also have a brief description of the existing conditions on site so we can all be confident that the spec will work. | Added additional text for herbicide application, ground conditions to be confirmed by client. | Existing ground conditions on site: The Boorley Gateway development was formerly green open space belonging to Braxells Farm. The ground drained well from west to east following the gradient slope of the land. The development is now flat and ground conditions are suitable for the implementation of new hard and soft landscaping. We have drainage layouts to prove this. | Spec wording: Weed Control: All weeds shall be cut down and taken off-site to a tip found by the contractor. Approved translocated herbicide (glyphosate - e.g. Roundup) spray shall be applied to all areas of the site to eliminate any remaining green weed vegetation and where necessary during the growing season after the initial brush cut. Please change wording as per red text above. | Complete | Wording still not correct - change to read Weed Control: All weeds shall be cut down and taken off-site to a tip found by the contractor. Approved translocated herbicide (glyphosate - e.g. Roundup) spray shall be applied to all areas of the site to eliminate any remaining green weed vegetation and where necessary during the growing season after the initial brush cut. | Report Amended | Could not locate revised uploaded to Salesforce
3 | Para 1.14. Please change the figure 75mm to 50mm. | Wording amended. | See attached Landscape Specification
4 | Para2.10. This needs to be a clear and demonstrative statement of action, not merely a description of a type fertiliser | Wording amended. | See attached Landscape Specification
5 | Para 5.21 please change 75mm to 25mm. | Wording amended. | See attached Landscape Specification
6 | Para 3.12. The watering element is very important. Please add in another para after this as 3.12.2 or similar entitled ‘Watering after planting and during establishment,’ move the last sentence of 3.12 into the new para and add more detail, eg about extra watering during drought periods. | This is already covered within the management plan. | See attached Landscape Management Plan | Add cross reference to management plan here so can't be missed. Their is still Insufficient detail. What does 'well watered' mean? Please add in the min. litres per tree that are required each watering visit. | Completed (9.20 in Man plan)
Landscape Management plan
| There are a lot of references to the LPA and EBC maintaining adopted land, but I’ d have expected that most of the open space would be adopted by the Parish. (Liz: I note Landscape’s comment about it likely to be the Parish Council who maintains land rather than the Borough Council, but as this is not yet confirmed I would simply amend the 2nd bullet point in paragraph 4.1 to add “(or the Parish Council if onward transferred to them)”, or something similar.) | Wording amended. | See attached Landscape Management Plan
| 7.4; 7.5 and 7.6 Please revise to ensure each para graph specifies the removal of all cut grass, after a suitable period after cutting for seed drop in September/October cuts. | Amended to comment. | See attached Landscape Management Plan | Sept/Oct cut - Period allowed for seed drop not yet noted. | Completed - see Updated landscape man
| 7.9 This paragraph need to be augmented. Please state the total number of herbaceous forbs within the wildflower seed mix. Please then work out a scheme for ensuring the species richness of the wildflower areas. For example, state what percentage of the species must still be present within the sward after 3 years. Then define the method of assessment, e.g. by 1m2 quadrat survey. Finally define remedial measures if the species richness has declined to an unacceptable level. This needs to be more than just weeding! | The wildflower mix will naturally develop to the receiving environment and which vary dependant on soil, implementation and environmental conditions in association with soil fertility these factors will determine the character of the grassland as stated bythe supplier. The mix is set out in the landscape specification and defined by the supplier. Text inserted: A comprehensive inspection of all the wildflower areas on site should be carried out by a competent person following establishment during the first, second and subsequent years in line with supplier recommendations. | See attached Landscape Management Plan | Information provided is not sufficient. Add full details including performance target, measurement technique (using quadrats) and details of remediation measures. | Updated landscape man plan to reflect remediation measures should wildflower fail | Outstanding - need details of how species richness of wildflower areas can be measured long term | Report amended | The wording included is too vague…please review and include clause that is measurable and enforceable. Refer to my previous comment on Sept 12th.
| 8.3. Please insert the highlighted text in the following sentence; Whip tree planting will provide potential replacements for larger standards if they were to fail after the first 5 years, during which time they must be replaced. | Amended to comment. | See attached Landscape Management Plan | I could not locate Native Woodland Planting areas on plan? Are these the same as native mix shrub planting? Not included on planting schedule. | For clarity the native mix referred to is in line with the outline approved and termed ‘Native tree and shrub planting’ mix.
| 8.8 Please inert the word ‘Damaged’ a the start of this paragraph. | Amended to comment. | See attached Landscape Management Plan
| 8.13 The thinning programme should be specified. Its not acceptable to delegate this to an un-named contractor in the future. | Additional wording to maintenance schedule | See attached Landscape Management Plan | Thinning operations - clause still worded vaguely. We want to avoid vigorous species swamping slower growing varieties. Please add further detail. | Completed
| 8.14 ‘All trees are to be maintained as standards with rotational coppicing to create structural diversity. No more than 10% of the trees should be coppiced in a single year.’ Please review this and clarify- are their not some standards in these areas to be retained as principal trees? Plus this negates what you say in paragraph 8.3. | Amended to comment. | See attached Landscape Management Plan | It does not seem that Mark's point has been addressed. We want to avoid the impression that ALL standard trees will be coppiced. Surely some standards will be left to establish as principle trees? Please clarify. | Completed
| NEW 8.22- Please insert a paragraph about watering. This should re-state the establishment period watering and then add a period during which watering is to be undertaken during period of drought | Amended to comment. |  | No definition of what is a period of drought . Please specify number of days without rain when watering should commence. Also specify min. litres per plant. | Completed
| 9.17. I’m not sure about the last sentence. Might be better if you add the following to the end; ‘where planting is within road junction sightline splays’. | Amended to comment. | See attached Landscape Management Plan
| 9.20. Please introduce a section on how the shrub areas particularly should be thinned. | This is already referred to in section 9.16. | See attached Landscape Management Plan
| 11.9- Please delete the words ‘months of June to August’ and replace with ‘growing season’. | Amended to comment. | See attached Landscape Management Plan
| 12.8 Please re-write this to clarify which management agencies are managing what. I don’t think Woking Borough Council who you have referenced here will be too interested in this site! | Amended to comment. | See attached Landscape Management Plan
| 12.11- 12.16 Aren’t these paragraphs superfluous? | Amended to comment. | See attached Landscape Management Plan
| 13.0 First line: Please delete the words ‘months of June to August’ and replace with ‘growing season’. | Amended to comment. | See attached Landscape Management Plan
Hard landscape Proposals- series 12
General points
1 | The plans generally lack sufficient detail and should identify the means of retaining surface construction and defining spaces, including all kerbs or edge details. The materials for these should be clearly specified. | Please see Engineer plans contain details of kerbing or edging | See drawing 6663-MJA-SW-XX-DR-C-200-C2 Highway Construction Details
2 | Please supply plans to demonstrate how the precinct and car park area will be drained and the details of gulleys, or include on hard landscape plans. | Please see Engineer plans contain details of drainage (illustratively shown on hard landscape proposals series 12) and gullies design | See plans approved under condition 9 6663-MJA-SW-XX-DR-C-001-C9 Engineering Layout Sh1 & 6663-MJA-SW-XX-DR-C-002-C11 Engineering Layout Sh2
3 | The distinction between adopted and unadopted parking spaces is not one that we are happy to have demarked though different paving colours. Demaracation of resident’s verses visit and communal spaces would be acceptable, but this does not seem to be the case in the drawings. | The material palette is in accordance with the details agreed in the outline proposals. |  | Looking at the outline proposals plan LA700 F it appears the materials palate has changed e.g. colour of blocks and as Mark points out same colour of blocks shown for parking bays across site! Also colour of blocks Autumn Ochre - drawings to be amended to follow out plans. Use of charcoal blocks will provide too little definition versus tarmac and brindle block colour too predictable. | The use of Charcoal and Brindle mix as opposed to the approved layout material of Autumn Ochre, is down to lack of availability/supply issue. Vistry think the Charcoal and Brindle mix is sufficient and will not have a lack of definition from the adjacent tarmac. | We remain concerned with the use of Charcoal blocks and would ask for this to be changed as there are significant areas paved with this colour of blocks | Vistry has previous notified the LPA of colour change due to availability, to soften the colour palette in line with the latest comment, we are suggesting introducing the brindle to the pedestrian block paved areas and the parking bays only.
4 | Please increase the difference between the symbol for 1.8m fences and 0.45m high knee rails. | Drawing adjusted accordingly |  | Not yet done - symbol still too similar green line. | Completed, addressed previously, comments relate to a previous version of our plan
VYH23647 12 Sheet 1
1 | Please correct the wall symbol to show colour all along. The text ‘1.8m High Brick wall to engineer’s specification’ does not give sufficient detail. Please supply a construction detail for this. |  | See submitted wall specifications
2 | I’m not convinced that a gabion wall construction to support the car park in front of the shops. As such an important structure this should have a more long term and attractive solution, even if the aim is to establish a hedge inform of it. Please supply a section through this area from the back of road kerb to the shop frontages, with an alternative solution/s. | Hedge planting to back of wall along with adjacent tree planting will soften and delineate the edge of the open space, gabions will provide a softer aesthetic than solid retaining wall and provide opportunity for invertebrate habitats to develop over time. |  | I suggest ACD add creeping plants along base of hedge planting to scramble over and soften gabion wall. Construction detail - I am content with a gabion wall detail assuming Vistry supply details for approval of selected stone facing (i.e. type of fill to gabions). | The stone type to fill the gabion walls will be 6N/P | Please clarify what 6 N/P is? Supply an image for approval | Class 6N/P material is an engineered fill material as specified in MCHW – Specification for highway works in accordance with Cl 626, the gabions are also designed to achieve 120 year design life.
3 | Please also supply a longitudinal section of the precinct area from SW to NE. | Vistry to advise. |  | No longer required.
4 | Please add in proposed levels for areas where these are missing. | Please see engineer plans for levels. | See plans 6663-MJA-SW-XX-DR-C-001-C9 Engineering Layout Sh1 & 6663-MJA-SW-XX-DR-C-002-C11 Engineering Layout Sh2
5 | The paving for the pedestrian area in front of the shops should be formed of a higher quality material, such as clay brick | Charcoal Keyblok proposed material continues the shared surface aesthetic, this has improved upon the original approved tarmac surface as requested by Tim when discussed. | charcoal blocks | Charcoal blocks too similar to adjacent tarmac. Will be bland. Introduce contrasting colour of blocks. As noted above the approved outline plans shows parking bays in Autumn Ochre colour. Introduce another colour of block that will visually lift the pedestrian area in front of the shops. This is a key focal space and should be carefully considered in terms of quality. | In terms of the hard surface treatment this is in line with MJA External works surfacing plan. The parking areas on Gateway are Charcoal and Brindle mix as opposed to the approved layout material of Autumn Ochre, this is down to lack of availability/supply issue. Vistry think the Charcoal and Brindle mix is sufficient and will not have a lack of definition from the adjacent tarmac. | We remain concerned with the use of Charcoal blocks and would ask for this to be changed as there are significant areas paved with this colour of blocks. The pedestrian area in front of the shops is a key space where charcoal blocks will not provide sufficient visual interest. NOTE: change key on all hard landscape plans as at present says charcoal buff paving slabs! Needs to be buff coloured. | Vistry has previous notified the LPA of colour change due to availability, to soften the colour palette in line with the latest comment, we are suggesting introducing the brindle to the pedestrian block paved areas and the parking bays only. | It is unfortunate that a more subtle colour of block paving cannot be sourced to provide the scheme with greater distinctiveness. I am surprised to hear that other colours than Brindle are unavailable? Please supply paper trail that this is the case and that Brindle paving is not a cost engineered solution!
6 | Construction detail for 0.45m High Metal Trip Rail required. Consider using this also for the steel replacement for the timber knee rail. | Vistry to confirm |  | A steel detail is required. Short lived timber 'birds mouth' details are not acceptable. | As above - timber knee rails have been approved on parcels within the main site
7 | Please identify add a post box to the plan near to the shops. Perhaps instead of the bollard next to the northern-most disabled parking space? | Vistry to confirm |  | Still outstanding - please add. Mark feels strongly this should be provided to avoid future residents being disenfranchised. | This is not a landscaping requirement and will be considered by the client in discussion with RM
8 | Please reduce radius on to the large planter within north east corner of the car park. | Vistry to confirm |  | Still outstanding. | Can’t find evidence of a planter | This is the planter | The radius of the planter reflects the road layout, if the radius is to be reduced the road layout will need changing, The radius of the kerb is what is required for the highway design
9 | Regarding this and similar legends in the key: - Keyblok paving to adoptable finished carriageway and shared surfaces in brindle, laid in herringbone pattern with white blocks to demarcate parking spaces, from Marshalls or similar and approved. Laid in line with engineer's details. As these are planning drawings, not contract drawings, we need to know what the products are. Please remove the phrase highlighted above from each relevant legend. | or similar and approved' removed
10 | Please locate lanterns lighting the shopping precinct on the building frontage | Lighting design to be provided by lighting engineer. | See 6663-MJA-SW-XX-DR-C-005-C2 Street Lighting | Street lighting plan only shows 6m high columns. Please provide details of wall mounted lanterns to building frontage. | Lighting to be provided by lighting designer or architect if attached to building. | Please supply copy of lighting layout | Plan showing the lighting for the site as per condition 8 have been submitted. External elevation lighting is to be agreed with the final providers of the retail units with details to be submitted once the final users have been agreed.
11 | Please confirm that the green dotted line on the plan represents the metal trip rail. | Green line corelates to the key for metal trip rail. |  | On key the green line is not dotted? Please change. | Comment addressed previously – these comments looked like they have been based on older revisions of the soft landscape proposals
12 | Please supply plan to demonstrate how the precinct and car park area will be drained and the details of gulleys | Please see Engineer plans contain details of drainage (illustratively shown on hard landscape proposals series 12) and gullies design | See 6663 Boorley Green SW Tech Note
13 | The bollards in the NE corner of the car park in front of the shops are rather stuck out in line with the likely pedestrian desire line from the estate. Please adjust their locations to the end of the parking spaces. | The bollards are placed to allow clear access between disabled bays walkways and do not obstruct the entrance way and are a minimum 2.5m clear of the building facade. |  | 2 bollards at the end of the 2 most N bays to be moved circa. 0.3m to west so tight to end turning space. |  | Outstanding comment | Close as possible but not inhibiting turning area | Please note my concern ref. heights of bollards above
14 | In the same area, NE of car park- please extend the area of block paving to align with the pedestrian path junction just north of the bollards referred to above. | Drawing adjusted accordingly.
15 | It would appear that you have some parent and child spaces opposite the disabled parking spaces. Can you please annotate which these are and also clarify how they and the disabled spaces will be marked. | Vistry to confirm markings | See R-F annotation | Add meaning of annotation R & R-F to key for clarity. Vistry to confirm markings to be used…white lining to be avoided. |  | Please confirm how these bays to be marked - avoid white lining | We have specified in line with engineer’s details and where in there is highway design such as the visibility of marking, we need to defer to the highway engineer in regard to marking of the bays. To be approved under Condition 25 of Pre-occupation conditions.
16 | The use of charcoal coloured concrete blocks is not supported because this will create a rather dark appearance in an area which will be heavily shaded in winter. | The original surface was tarmac a far darker colour the current surface was agreed with Tim. Client to confirm they are happy with the change in colour to natural (neutral grey is currently not a Marshalls colour option). |  | See comment 5 above - change Charcoal blocks. | still to be made | Using a block colour other than Charcoal is an important change that needs to be made | Vistry has previous notified the LPA of colour change due to availability, to soften the colour palette in line with the latest comment, we are suggesting introducing the brindle to the pedestrian block paved areas and the parking bays only.
17 | Details needed for the brick wall and brick retaining wall. | Engineer to provide retaining wall and wall detail. | See 6663-MJA-SW-XX-DR-S-1171-Retaining Wall Details
18 | Please clarify the purpose of the bollard in the far north of this plan towards the start of the path. I’m concerned that whilst it may help reduce the risk of speeding cyclists, it will also impede access by mobility scooters. Ditto the bollard at the SW corner of the carpark at the start of the entrance path there. | The bollard placement is intended to inhibit potential vehicular ingress into the open space along the 3m wide path adjacent to the open space hedge and trees. The bollard are 125mm width placed in path centre which will should leave adequate space for mobility scooters.
19 | The large areas of planting within the shopping precinct area are important and should be surrounded by low brick walls to prevent trampling. We’d need the construction detail for this wall too please. | Hedges have been place to the back edge of the planting which will have a galvanised wire structure (see key) to stop cut through. A proposed wall is unnecessary and would reduce the planting area, add to the hard standing and reduce the chance for natural runoff into the soft/planted areas. |  | Use steel knee rail to protect planting in this bed | See previous comment | Not yet addressed - the planting beds require some protection | Planter details provided | A brick raised planter detail would be preferred for longevity similar to detail on hard landscape details sheet. If the brick wall is 450mm high it will double as informal/occasional sitting wall.
20 | Please clarify the legend ‘R’ and ‘ R-F’ on the plan. | R=Retail & R-F=retail family
21 | Please clarify what the boundary detail is to the back (east side) of the car park behind the shops. It would appear that this is a brick retaining wall. It will require some sort of railing along the top beside the path for safety reasons if the wall is higher than 600mm. | Refer to engineer details for retaining wall details. | See 6663-MJA-SW-XX-DR-S-1171-Retaining Wall Details | Looking at the retaining wall details sheet I cannot work out the type of wall in this location? Please add to the hard landscape plans notes locating wall detail types for each section of walls. | Changed to brick wall
VYH23647 12 Sheets 2, 3 and 4
1 | Regarding this and similar legends in the key: - Keyblok paving to adoptable finished carriageway and shared surfaces in brindle, laid in herringbone pattern with white blocks to demarcate parking spaces, from Marshalls or similar and approved. Laid in line with engineer's details. As these are planning drawings, not contract drawings, we need to know what the products are. Please remove the phrase highlighted above from each relevant legend. | 'or similar and approved' removed
VYH23647 12 Sheet 4
1 | This plan has a third type of paved surface for parking – tarmac. Please clarify the design thinking behind the use of three different types, which is not acceptable because it over complicates the design. | There is no material difference and we have previously clarified this is for visual effect within the drawing only |  | What is the difference between tarmac & impermeable tarmac on key? This is confusing - combine the 2 types unless specific reason otherwise. | Combined
2 | Please co-ordinate this plan with the soft landscape plan for this area by including the area of Breedon gravel ion the community garden area on the plan and key. Note this reads; Proposed self-binding gravel through open space and natural green areas and (Breedon Golden Amber, or similar and approved) Please delete the phrase ‘or similar and approved’ |  |  | Not yet done. Show Breedon gravel paths on hard landscape plan and add descriptive note omitting 'or similar approved'. Clarify proposed edging - suggest pinned steel edge to create smooth curves of path. | Completed
Ecology | Ecology have requested that section 10.4 be amended to read; Hedgerows are to be cut on a 3-year rotational basis to maintain a constant supply of flowers, fruits and seeds for the benefit of wildlife. Each side and the top can be cut in successive years or 1/3 of the hedgerow can be cut in successive years. | Document amended | See attached Landscape Management Plan
| Sundry other points - show bench and bin positions on hard landscape proposals plans to ease coordination. |  |  |  | These are shown on the soft landscape plans which is sufficient detail | I do not agree. Please show these on the hard landscape plans | Shown on Series 12 - hard landscape plans
| Check 4x hard landscape proposals plans as some areas of underground attenuation tanks not shown (symbol extract below)…e.g. sheet 1 |  |  |  | The latest drainage is reflected within Hard Landscape Proposals Drawing 12 and Sheet 4 illustrate the underground attenuation – drainage condition for this site has been approved