## Sheet1
Phase 1H/1i Comments on layout
Overall Layout | Responsibility | JB Comments
The overall layout is generally considered to be acceptable, however various detailed points still need to be addressed.
Internal Space Standards and Accessibility Standards
Local Plan Policy DM30 “Internal space standards for new residential development” requires all new dwellings to meet the Nationally Described Space Standards (NDSS). It is still not considered that the plans and schedule demonstrate compliance with the NDSS, particularly house types Braxton, Clarkston, Crosswood, Denton, Faverwood, Fordwood, Type 3 and Type 4S. However, it is acknowledged that the house types approved under the original reserved matters application did not fully comply with the NDSS given the local plan policies in place at the time, and therefore it would not be reasonable to refuse this application on that basis. As such no further amendments are requested on this occasion. |  | Noted
Rear Access
The rear accesses are now appropriately shown on the Site Layout, Enclosures Plan and Landscape plans but the Refuse Plan is not consistent with them and the following amendment is required: | AAP | These have now been amended
• The rear access for plot 132 has been moved to the side boundary adjacent to the rear elevation but is still shown at the rear of the garden on the Refuse Plan. | AAP
Landscape
It is noted that the tracker spreadsheet responding to the previous feedback says that some tree species have been changed following analysis of tree species and foundations to ensure survival and establishment of trees. It is noted however that the changes have included replacing the Tilia cordata “Green Spire” 16-18cm proposed along the length of the main road running through the between Phase 1h and 1i with Carpinus betulus Lucas 16-18cm and Magnolia grandiflora “Exmouth” 16-18cm. The Tilia cordata “Green Spire” are proposed along the full length of the main road throughout the Boorley Gardens development. These trees are to be planted in the highway verge and therefore should not be affected by foundations. All these trees need to be changed back to the Tilia cordata “Green Spire” 16-18cm. | ACD | Please see ACD Explanatory Note justifying the replacement of trees.
In addition it is noted that there are some changes to the proposed tree species on the side roads however these are not all acceptable and some amendments are required:
Adjacent to plot 114 – proposed change from Sorbus aria “Magnifica” 14-16cm to Prunus “Amanogawa” 14-16cm is not appropriate as the substitute is too small in foliage volume. The proposed change is acceptable in the other locations given the trees’ position to the south of the adjoining garden. | ACD | this has been changed back to Sorbus aria “Magnifica”
Adjacent to plot 124 – proposed change from Acer Campestre “Elsrijk” 14-16cm to Sorbus aucuparia 14-16cm is not appropriate because the substitute is too short lived. It is suggested that another Acer Campestre cultivar is used, such as ‘Streetwise’ as this is thought to be a slimmer tree. | ACD | this has been changed to Acer Campestre 'Streetwise'
Adjacent to plot 162 – proposed change from Acer Campestre 14-16cm to Magnolia grandiflora “Exmouth” 14-16cm is not appropriate due to winter shading. It is suggested that another Acer Campestre cultivar is used, such as “Elsrijk” or “Streetwise”. The proposed change is acceptable adjacent to plot 142 due to its position in relation to the nearest dwellings. | ACD | this have both been changed to Acer Campestre 'Streetwise'
North of plots 179 & 180 – proposed change from Betula ermanii 14-16cm to Sorbus aucuparia 14-16cm is acceptable provide one of the larger cultivars is used, e.g. “Sheerwater seedling”. Please annotate this on the plan. | ACD | Now annotated on plan
East of plot 182 – proposed change from Sorbus aria “Magnifica” 14-16cm to Sorbus aucuparia 14-16cm is not acceptable as this site needs a good-sized medium tree and Sorbus aucuparia the species, although a similar size, is very uneven in shape. An Acer Campestre would be appropriate here, but it should be moved to the north of the adjoining footpath so it is in the open space. | ACD | Now added Acer Campestre and moved
The other changes to the landscape proposals are acceptable but please make the following amendment: • Where the rear access gate for plot 124 has been repositioned closer to the garage to avoid conflict with the proposed tree, the soft landscaping underneath tree needs to be reinstated. | ACD | Now amended
Streetscenes
To avoid inconsistencies with the house types, please make the following amendments to the streetscenes: • Amend streetscene 2 to show a standard window above the front door on plot 182 to reflect the changes made to the Fordwood house type, as has been done for the other Fordwood plots. | AAP | This has now been added
Affordable Housing
The Tenure Plan rev C has been amended to remove reference to any of the affordable housing plots, however this is not appropriate as some of them are covered by this application, e.g. plots 114-116 and 187-192. Please amend the plan to show the tenure of all plots included within the application. | AAP | Now amended to include full tenure mix
Road and open space adoption
It is noted that the Adoptable Areas Plan and Maintainable Open Space Plan have been submitted but these show that some street trees are not to be managed by Hampshire County Council or a management company, e.g. trees adjacent to plots 109, 111, 114, 124, 125, 134, 135, 142, 144/145, 148, 162, 169, 172, 174, 175, 178, 182, 185, 187 and 192. Please amend the plans to include these trees in communal management, rather than private management. In doing so please make ensure the annotation/shading used makes it clear that the trees are included within the areas to be maintained by the management company. | PFA / Miller / Luken Beck | This has been amended and is provided.
Inconsistencies
The drawing reference for the latest version of PH1H_1i_TYPE2_S1_E1 has not been changed to rev D in the drawing number, despite rev D being listed in the description of amendments above. | AAP | Now amended to Rev. E
Application boundary
The red edge defining the application boundary needs to be amended to include the parking to the east of plots 103-109 as the position of the visitor parking has changed. In addition the red edge needs to include areas where additional tree planting is now shown along the northern, eastern and southern boundaries as it has been proposed as mitigation for loss of tree planting within the parcel that was previously approved. | AAP | Red line extended to include these areas
I hope the above comments in relation to the overall layout are useful. In submitting any amended plans in the future please provide an indication as to the matters you have addressed, and which, if any, you have been unable to satisfactorily resolve. If there are any instances where you have not been able to address the issues raised, please explain why this has not been possible.