## Sheet1
Phase 3D commentas
Overall Layout | JB Comments to EBC
The changes to the overall layout are generally considered to be acceptable, however the dwelling on plot 668 needs to be repositioned as currently the 1st floor study window looks directly into the rear garden of plot 445. In amending the layout, please also add the annotation for the house type proposed on plot 448 and the bay window on the side elevation fronting the road on plot 452. | Done
As a result of the amendments to the layout please submit a revised levels plan and update the Garden Area Schedule so that it gives the necessary information for the revised house types on units 462 and 668, as these have not been updated. In addition please revise the title of the document as the latest version refers to both rev A and rev B. | Done
NDSS and Accessibility Standards
Whilst the Nationally Described Space Standards (NDSS) compliance schedule has been amended to include floor areas and widths of bedrooms the table is misleading and unclear. In some instances the dimensions given are the maximum width and length of the room (even if the room is not rectangular in shape), and in others even when the room is rectangular in shape the dimensions given do not result in the floor area listed, e.g. 3.4 x 3.3 = 11.22, not 11.5 as listed. | We have added dimensions to the floor plans to illustrate the room sizes. If you are able to advise if you arent content with this approach that would be appreciated. | Discuss - I assume this provides all of the information you need?
In addition it is not clearly shown on the floor plans which areas are being included as in-built storage. There appear to have been assumptions made about built-in wardrobes without them being shown on the floor plans, e.g. the schedule states that 3.21 sq.m. of built-in storage is provided for the Beauwood house type, but the floor plan only shows 1 small storage cupboard and a possible airing cupboard (although the walls aren’t complete) on the first floor landing, which is less than 3.21 sq.m. Please re-check all the figures and calculations in the schedule and amend the floor plans to ensure they do meet NDSS and show all the built-in storage proposed. | Annotation added to plan
As previously requested, please could you confirm if all units comply with M4(1) standard (Visitable dwellings). | All bedroom sizes are Miller NDSS and building regulations compliant.
Landscape Proposals
The soft and hard landscape drawings are still not consistent with regard to the surfacing of paths/service margins. The hard landscape proposals show a footpath on both sides of the road leading into Phase 3D, but the soft landscape proposals show a grass verge on the eastern side of the road. | Now Amended
In addition, as previously requested, all of the road serving Phase 3D should be block paved, as originally proposed. In amending the surfacing please look at the interface between the different surfacing materials, as the current approach at the southern end of the parcel has a number of awkward juxtapositions. | Now Amended
Drainage
Whilst the drainage plan has been submitted it appears to show a drainage run conflicting with tree planting proposed to the west of plots 448 and 668, although the tree planting shown on the drainage plan is not consistent with that shown on the soft landscape proposals. Please amend the drainage plan to accurately reflect the proposed landscaping in order to demonstrate the proposed tree planting is viable. In addition please confirm that the revised drainage proposals do not alter the volume or rate of flow of surface water from this parcel into the wider drainage infrastructure. | Now Amended
Materials
The key refers to different coloured painted brickwork for Area 1 and Area 3, but the area number is no longer indicated on the layout as it was on earlier versions of materials layout. Please amend the key to refer only to the materials proposed in Phase 3D and remove the reference to areas in the wording of the key for painted brickwork and boarding. | Now Amended
Streetscenes
The first and fourth streetscenes shown on drawing 817072_PH3D_STREETSCENE_01 rev B “Street Scenes – Sheet 1” are inaccurate with regards to the house types proposed on plot 462 and 668. In amending the streetscene please remove the trees that are shown in front of all dwellings as it prevents the full assessment of the proposals. | As we have amended the elevations for Fordwood in Phase 1H/1i, we have updated these elevations and floor plans
Road and open space adoption
As previously requested, please provide a plan showing which areas are to be offered for adoption, and which are intended to be managed and maintained by a private management company. | Provided road adoption plan and open space adoption plan.
Residential Amenity and Plot by Plot comments
To ensure the layout does not have an adverse impact on the residential amenities of the occupiers and that the various plans are consistent with each other, please make the following amendments:
• Plots 445, 446, 449 & 450 (Clearwood house type) - the bedroom 1 en-suite and bathroom windows should be annotated as obscure glazed on the floor plan as well as the elevations for all plots. In addition, for plot 450, the bedroom 2 en-suite needs to be annotated as obscure glazed with any opening part being top hung only on the floor plan as it is on the elevation. | Floor plans now reflect elevations
• Plots 447, 448, 451 & 668 (Fordwood house type) - it is noted that the house type has been changed to introduce a faux window at first floor level above the front door. Please can you confirm if a glazed window frame is to be installed and if so whether it would be obscure glazed or not. Do you have photographs of where this approach has been used elsewhere? | Plans now on file and amended
• In addition the floor plans and elevations are not consistent with the layout with regard to the handing of plot 668 and the version of drawing 817072_PH3D_FORDWOOD_U1_E2 rec/d on 11.11.24 refers to rev C in the description of the revisions, but the drawing reference is not clear and neither are the plot numbers. Please amend the labelling so it is clear. | Now amended
• Plot 452 (Braxton house type) - the bathroom and en-suite windows need to be annotated as obscure glazed on the floor plan as well as the elevations. In addition, as previously requested, the landing window needs to be annotated as obscure glazed with any opening parts being top hung only, on the floor plans and elevations, to ensure no loss of privacy for plot 453. | Now amended
• Plots 455-458 (Baymont house type) - the revised pairing of house types has addressed the previous point about the unbalanced elevations and discordant features in the streetscene. However, an additional small window needs to be added to bedroom 1 on these units as the expanse of window to void is too large as currently proposed for these pairs of semi-detached units. | Now amended
• Plots 459-460 (Lockton Special house type) - the revised pairing of house types has addressed the previous point about the unbalanced elevations and discordant features in the streetscene. However, bedroom 1 needs to be served by two windows as the expanse of window to void is too large as currently proposed for this pair of semi-detached units. | Now amended
• Plot 461 (Hampton house type) - the floor plans and elevations are not consistent with regard to the size of the lounge and bedroom 2 windows; or the position of the en-suite window. | Now amended
• Plot 462 (Beauwood house type) – the floor plan appears to be missing the wall surrounding a possible boiler cupboard, otherwise there are 2 doors into bedroom 4. In addition the floor plans and elevations should be amended to show the house type as handed, to be consistent with the site layout. | Now amended
• As previously requested, all dwellings or pairs of semi-detached dwellings should have chimneys as was originally approved. Please add chimneys to the party walls on plots 455/456, 457/458 and 459/460 as it is not appropriate to reduce the quality of the development via the NMA process. | Now amended