## Sheet1
Phase 1H/1i Comments on layout
Landscape | Responsibility | JB Comments
Whilst a revised version of the previously approved Open Space Proposals – Sheet 3 drawing has been submitted, as requested, it cannot be approved as part of this application as it shows a large area of what should be useable open space as being covered with Proposed mitigation native mix shrub planting. It is not clear what it is mitigation for, and in any event this is not acceptable as it significantly reduces the amount of useable public open space and would mean that insufficient on-site open space would be provided. As details of the proposed open space need to be agreed under Schedule 6 of the S106 I suggest that the Open Space Proposals – Sheet 3 is not considered as part of this application to ensure no further delays to the determination of this application. The Acer Campestre that was moved from east of plot 182 into the open space can be shown on any plans submitted to meet the S106 obligations. |  | Plan to be removed and considered under S106 obligations
Road and Open Space Adoption
The amended Maintainable Open Spaces Plan (M434/205) is still not consistent with the latest landscape proposals with regard to the tree planting between plots 174 & 175 and the planting on the southern and eastern boundaries. It is also noted that the Maintainable Open Space Plan shows the line of the water main and some of the planting shown on the Soft Landscape Proposals appears to be very close to it. Please confirm that there would not be a conflict between the tree planting shown on the latest landscape plans and the water main as this tree planting has been proposed as mitigation for tree planting lost from within the site as a result of the re-design. | DB - PFA JBed - Miller | Plan amended with revised planting so trees are not in conflict with the water main
Drawing Register
Changes required to Drawing Register | JB - Luken Beck | All changes now made