## Landscaping Comments
|  | EXTERNAL MATERIAL SCHEDULE Rev C | Please note - this Schedule is to be read in conjunction with all of the following:- Eastleigh Borough Council/Amiri Construction Specifications, MH Architects Ltd Drawings, Arch Associates Ltd Civil & Structures Drawings, M&E Drawings, Solas Realta Fire Strategy Report/Deacon Designs Landscaping Documents
Landscaping comments provided by Tim Griffin to Rebecca Altman following DoC submission on 08/08/25 (RA provided to AHz on 05/09/25)
Last updated: 05/12/25 (AHz)
Revision: B
PLANTING PLAN REV E | Tim Griffin Comments of 21/08/25 |  |  | ACL Response | Tim Griffin Comments of 14/11/25 | ACL Response
| Tree Planting - successful delivery of the tree planting is critical to the landscape setting for this project. Whilst the general arrangement of trees is acceptable, I am not clear why some trees have not been planted in the location below to soften the frontage to Queens View? There appears to be an opportunity to plant a line of 3 trees here. |  |  | The Highways Authority have confirmed that trees should not be within 2m of an adopted footpath and should not be planted within 5m of services. | The Amiri spreadsheet states that tree planting in this location is not possible as 'The Highways Authority have confirmed that trees should not be within 2m of an adopted footpath and should not be planted within 5m of services'. I don't understand this comment since there are 2 trees planted in a similar location to the SW(see snapshot below): Also, any issues with services can be overcome by installing a vertical root barrier. At least 2 trees must be planted to soften an otherwise completely open view of the car park from the main road. | We have consulted with Deacon Design again on this point and they have confirmed that the trees which Tim is referring to are set back 2m from the adopted footpath and there are no services in this location. The area where he has suggested adding three trees will not be possible because the trees would be less than 2m away from the footpath and there are existing services running in this area. The installation of a vertical root barrier is therefore also not a possibility.
| Please omit the Amelanchier tree here as it is too tight to the building and will crowd the adjacent Prunus app.tree. |  |  | Deacon Design have confirmed as follows:- "This tree was selected for it's narrow form. After 50 years it will grow 1.5m radi (Source Hillier Trees Guidance) therefore it will not compete and will not cause management issues. DD recommend retention. We also need to be mindful of retaining tree quantities to achieve BNG requirements". | Deacon Design have said this tree only grows to 1.5m radi after 50 years. In reality, I think this is an underestimate in most locations, but since the tree is planted so close to the buidling line it may achieve a limited size. No change.
| Some changes to tree species are required as there is an over-reliance on Birch. |  | Replace 2 x Betula 'Edinburgh' in norther corner of site with 2 x Amelanchier 'Robin Hill' Single Amelanchier spp. In parking area planted in small bed with limited rooting zone - replace with more robust species please. All trees in grass to be supplied with black strimmer guards. | Deacon Design have confirmed as follows:- "Species selected has narrow form and is selected for its tolerance of urban conditions, low impact on foundations (low water demand). DD recommend retention. Single Amelanchier spp is the only tree with root volumes that fit this location. DD recommend retention. We agree that all trees are to be supplied with black strimmer guards" Please see attached updated Detail. | As the space is tight in the northern corner, leave as Betula spp, however, change tree species adjacent 6 parking bays in W with 2 Capinus 'Lucas' along road frontage and 3 x Magnolia as per mark up above. There is no space limit here and Betula is a short lived species. Although technically root volumes may be limited in this situation, in reality trees will exploit wider/deeper subsoil. Amelanchier does not cope well with locations dominated with hard surfacing. Species such as Carpinus 'Lucas' or Acer camp. Elsrijk should be specified instead. | Please see updated plan which now reflects Tim's choice of trees.
| Native mix hedges |  | These are important elements of planting to soften the development edge. Species mix presently rather odd (Vib . Op. listed twice!) Please change mix to include min. 30% Hawthorn plus 10% evergreen species for some year-round effect. All species planted at min. 80-100cm high. | Please see attached updated Planting Plan, Deacon Design have added 4 hedge species- Lonicera, Euonymus, Ligustrum and Corylus. | Please replace Lonicera periclymenum with Acer campestre (as per Lisa Malter comment). The Lonicera is a vigorous rambling plant that could overwhelm other plants in the hedge. | We have discussed this with Deacon Design and they are of the opinion that honeysuckle is not invasive and has been requested here by the project ecologist.
| Please double the number of Euonymus alatus to close centres between plants to soften this sensitive edge. |  |  | Please see attached updated Planting Plan, Deacon Design have added 4 Myrtus communis for a colour contrast to the Euonymus alatus. | No comments.
| Please review shrub planting as over-reliance on Vib. Davidii and Skimmia 'Kew Green'. |  | Introduce some further reliable shrubs to add variety to scheme (e.g. Variegated evergreen spp.). | Please see attached updated Planting Plan, Deacon Design have reduced the number of Achillea, Echinacea, Rudbeckia, Skimmia and Viburnum and added Abelia, Aucuba, Lavander, Nepeta and Sedum. | No comments.
| There are significant areas of perennial planting that will be relatively high maintenance. |  | Please confirm arrangements to ensure this planting will be maintained long-term. Without correct maintenance these beds will quickly deteriorate. | Deacon Design have confirmed that these are hardy perennials and simply require annual pruning. Please refer to Landscaping Management Plan for details. | No comments.
| Areas of strong lawn grass mixture internal to site replaced with species rich lawn turf (as per Ecology comments at full application stage). |  | Frontage to Queens View left as strong lawn grass (specify either turf or seeded). | Deacon Design have now included two types of grass – Amenity grass which is a strong Lawn Mix and a Species Rich grass which is a Meadow Mixture. Please see updated Planting Plan. | No comments.
| Please check no clashes between drainage/services etc and tree pits. |  |  | Services have been suitably coordinated. | Tree planting shown on the planting plan must be deliverable. Losses later on due to clashes with services/drainage etc will not be accepted. | It is our understanding that all planting comes with 5 year planting establishment /replacement conditions as part of the planning approval.
| Confirm no issues with external lighting proposals. |  | Loss of new trees on site will not be entertained due to clashes with services. | The Highways Authority have confirmed that there should be a 5m offset where we are planting trees near lighting columns. Please would you confirm whether this comment is in relation to the adopted lighting only? | No comments.
SOFT LANDSCAPE MANAGEMENT PLAN REV A |  |  |  |  | No comments.
| Update as required to reflect changes to planting plan as noted above. |  |  | Please see attached updated Landscape Management Plan. | No comments.
| 4.1 Watering - further details required (e.g, definition of a dry weather?). |  | Particular focus on watering new trees for first 2 years after planting. | Please see attached updated Landscape Management Plan. | No comments.
| Trees in grass to have black strimmer guard. |  |  | Please see attached updated Landscape Management Plan. | No comments.
| Perennial planting not yet covered by the management plan? |  |  | Please see attached updated Landscape Management Plan. | No comments.
TREE PIT DETAIL AND SPECIFICATION |  |  |  |  | No comments.
| Specify type/detail of tree fixing (biodegradable tie/band preferred). |  |  | Please see attached updated Tree Pit and Specification Detail. | No comments.
| Make clear root barriers installed tight to services/kerb lines NOT around edge of tree pits that would limit root spread/tree growth. |  |  | Please see attached updated Tree Pit and Specification Detail. | No comments.
| Check if a Terram membrane is requred at the base of the pit? I don’t usually see this included. |  |  | Please see attached updated Tree Pit and Specification Detail. | No comments.
EXTERNAL MATERIALS SCHEDULE REV A |  |  |  |  | No comments.
| Change block paving from light grey colour to more visually attractive colour that will contrast black tarmac (not Brindle but mottled Harvest shade of similar). |  |  | Please advise whether it could cause issue if the block paving was not amended? It would be the client's preference to retain the original choice to maintain a consistent palette, style and design throughout the development, as well as staying inkeeping with the surrounding area. Will this cause issue? | I remain of the opinion that some variation in surfacing colour would add interest to the scheme. | We are arranging for a sample block to be presented for physical review.
SUNDRY COMMENTS
| Please supply details of all enclosure/fencing types plus detail of retaining walls. |  |  | Please see attached updated Planting Plan. | I could not locate these. Only retaining wall shown on planting plan. | Please see attached Site Plan where you will note the F1/F2/F3 references which all denote fencing. You will also note the retaining wall shown on this plan too.
| Low post and rail fencing to ideally be steel estate railing detail (or similar) for longevity (could be colour matched to railings on building?). |  |  | Agreed. Please refer to Site Plan and see attached Planting Plan for locations. | Could not locate these on the site plan or planting plan. Please supply detail of this low post and rail fence as it is a key element along the boundary to the playing fields. | Please see attached Site Plan and the references to F2 showing the locations of low post and rail fencing.
| Supply details of proposed benches and are there any litter bins proposed? |  |  | There are no benches proposed (the site sits next to a community playing field/sports pavillion where there are benches available). There will be a litter bin placed outside the retail unit. | Where is the bin outside the retail unit that is mentioned? | Await updated site plan from MH Architects showing the location of the litter bin.

## Ecology Comments
|  | EXTERNAL MATERIAL SCHEDULE Rev C | Please note - this Schedule is to be read in conjunction with all of the following:- Eastleigh Borough Council/Amiri Construction Specifications, MH Architects Ltd Drawings, Arch Associates Ltd Civil & Structures Drawings, M&E Drawings, Solas Realta Fire Strategy Report/Deacon Designs Landscaping Documents
Ecology comments provided by Lisa Malter (Ecologist) to Rebecca Altman following DoC submission on 08/08/25 (RA provided to AHz on 09/09/25)
Last updated: 31/10/25 (AHz)
Planning Condition | Lisa Malter Comments of 08/09/25 |  |  | ACL Response
11 - Boundary Treatment | I do not see any documents relating to this Condition. Openings in the fences must have at least two gaps (15x15cm min) to allow the free passage of hedgehogs and other small mammals through the site. |  |  | The attached Planting Plan has been updated noting the installation of hedgehog highways.
14 - Biodiversity Enhancement & Management | The BEMP by Ecosupport (June 2025) is satisfactory and Condition 14 can now be discharged.
15 - Lighting | I have reviewed the lighting design by DW Windsor (rev B, July 2025). The lighting plan must show the proposed locations of bat boxes on the building and in the garden to ensure that these areas are kept sufficiently dark (1 lux or below). Bats forage on the vegetation, so the trees must also be dark enough. Light spill from the windows must also be taken into account. |  |  | Please see attached updated Lighting Deign Layout which now shows the bird and bat bricks and box. You will note the vertical grid to the West façade to check the impact of the nearby bollards on the bat boxes, it reads well below 1lux.
18 - Landscaping | The condition states that the landscaping plan shall incorporate sufficient flowering species to support wildlife. Condition 19 states that the landscape management plan is to include management of hedgerows and plant species to ensure year-round supply of flowers, fruits and seeds. This can only be achieved with a diverse mix of species which flower at slightly different times. |  |  | Please see updated Planting Plan and updated Landscape Management Plan.
| I have reviewed the Planting Plan by Deacon Design (rev E, June 2025). There are a few anomalies in the planting plan which should be explained: Species rich grassland has been recommended in the BEMP, however this is not shown on the planting plan. On p18 of the BEMP it states: The areas of species rich grassland on site are to be established through the sowing of a wildflower mixture such as Emorsgate EM4 - Meadow Mixture for Clay Soils or Emorsgate EM6 - Meadow Mixture for Chalk and Limestone Soils. I only see strong lawn grass mixture specified in the public areas and proposed private lawns to rear gardens with no grass mixture specified. If the private garden areas are to be sown with a wildflower grassland mixture, this should be written on the plan. However, this cannot be relied upon, as the owners could change the grass species composition, cover them with fake grass, or mow them at inappropriate times. As also requested by the Landscape Officer, Areas of strong lawn grass mixture internal to the site should be replaved with species rich lawn turf (as per Ecology comments at full application stage). Frontage to Queens View can be left as strong lawn grass (specify either turf or seeded). |  |  | Deacon Design have now included two types of grass – Amenity grass which is a strong Lawn Mix and a Species Rich grass which is a Meadow Mixture. Please see updated Planting Plan and updated Landscape Management Plan.
| The mixed native hedge is listed at the top of the diagram four separate species in roughly equal amounts (Carpinus betulus, Cornus sanguinea, Corylus avellana and Viburnum opulus) but in the other locations around the property the mixed native hedge is only comprised of three species: Carpinus betulus, Cornus sanguinea, and Viburnum opulus (listed twice and becoming the main species in the hedge). To satisfy Conditions 18 and 19 the mixed native hedgerow should contain at least 4 species, if not more. |  |  | Please see attached updated Planting Plan, Deacon Design have added 4 Myrtus communis for a colour contrast to the Euonymus alatus.
| I understand that the intent of the landscape architect is to avoid thorny species such as holly or hawthorn, but field maple could be introduced as an additional native hedgerow plant. |  |  | Please see attached updated Planting Plan.
19 - Landscape Management Plan | I have reviewed the Soft Landscape Management Plan by DD (rev A, June 2025).
| Soil testing is recommended before planting to ensure that the plant species can thrive in these soil conditions. What is the procedure to be followed to ensure that the soil test results and the plant species list is reviewed by the ecologist and landscape architect? |  |  | Deacon Design have confirmed that samples will be submitted to a UKAS accredited laboratory for a range of physical and chemical tests to confirm the composition and fertility of the soils. The results will be presented in Certificate format.
| The condition also specifies: to include management of hedgerows and plant species to ensure year-round supply of flowers, fruits and seeds. The boundary hedge mix planting section (p14) specifies To suit species - Three-year rotation and alternate sides should be cut in the first three years with the top cut within the third season, however it does not explain that this is to ensure a year-round supply of flowers, fruits and seeds and that pruning must be done only after flowering has finished, preferably in the autumn. |  |  | Please see attached updated Landscape Management Plan.
| The hedge trimming regime section from the BEMP section 4.3.4 should be copied into the Landscape Management Plan. |  |  | Please see attached updated Landscape Management Plan.